## Sheet1
Features | Require Time in Hours | From Date | To Date
User can see our ranking. | 150 Hrs | 2022-09-06 | 30/6/2022
User can not change tab feature while giving test if they will change tab quiz has been closed
Save the current state of the user if use not submit question then after completed time automatically submit and get score of user.
Users can select subject and give quiz according to their choice.
Admin can insert, delete, update questions User can check history.
User can select dificulty level of question according to subject

## Copy of Sheet1
Features | From Date | To Date | Require Time in Hours
Database and virtual environment - Set environment - Creating Databse | 2022-09-06 | 2022-10-06 | 15 Hrs
User Authentication - User registration - User login | 13/6/2022 | 14/6/2022 | 16 Hrs
Admin can insert, delete, update questions. | 14/6/2022 | 16/6/2022 | 26 Hrs
User can choice subject as well as dificulty level - Easy level - Mediam level - Hard Level | 17/6/2022 | 20/6/2022 | 18 Hrs
Leadership board for user module. -show ranking use base. | 21/6/2022 | 22/6/2022 | 19 Hrs
User can not change tab feature while giving test if they will change tab quiz has been closed - quiz end | 23/6/2022 | 26/6/2022 | 24 Hrs
Save the current state of the user if use not submit question then after completed time automatically submit and get score of user. - save state | 27/6/2022 | 29/6/2022 | 18 Hrs
User can check history. - Previous leadership board - | 30/6/2022 | 2022-03-06 | 22 Hrs
|  | Total Hour | 158 Hrs
Start Date | 2022-09-06
End Date | 2022-03-07
Total Hour | 158 Hrs